## Sheet1
				2015			2016					2017
Task nº	Task Denomination	Person*Month	Partner responsible for task	Acronym of partners involved in task	10	11	12	1	2	3	4	5	6	7	8	9	10	11	12	1	2	3	4
1	Kick-off meeting	0	Susana Cardoso	SC, AB, LM, PR, IM, PS, FM, BIC
2	Modeling stage1		António Balula	AB, IM, PS
3	Manufacturing stage 1	11.04	Luís Macedo	LM, FM, BIC
4	Characterization stage 1	15 e tal	Pedro Ribeiro
5	Modeling stage 2		António Balula
6	Manufacturing stage 2	8.25	Luís Macedo
7	Characterization stage 2		Pedro Ribeiro
		19.29